## 30%
30%
Disciplines/Deliverables | Survey/Data Capture | Street | ROW | Traffic | Sewer | Water | Utilities/LAB
Horizontal Alignment | Existing Centerlines: a) Split Curbing to find center or street. b) Set PKs in street CL. c) Use ESD data to obtain initial information and then validate in the field. | Existing Centerline: Use centerline provided by Survey. Proposed centerline: Created with engineered curves and based on found information in the field and record information from the ESD land base. | Existing Centerline: a) Provide record boundary information to be used by Field Survey when locating front pins and property boundaries | Create the following: Existing/Proposed Lane Config. | Review of Existing System. (If problem, then notify Project Engineer) | Review of Existing System. (If Problem, then notify Project Engineer. | Review of Existing System. (If problem, then notify Project Engineer).
Vertical Alignment | Existing Centerlines: a) Provide 3D information along centerline enabling Street group to be able to create an existing vertical alignment. | Existing Centerlines: a) Create from Field Survey data. Proposed Centerlines: Tie in centerline grades to adjoining streets, using engineered curves from predefined Design Criteria. |  | Create the following: Existing/Proposed Lane Config. | Review of Existing System. (If problem, then notify Project Engineer). | Review of Existing System. (If problem, then notify Project Engineer). | Review of Existing System. (If problem, then notify Project Engineer).
Survey Data | a) Use checklist provided from Engineering to collect data. B) Obtain record information from ESD regarding horizontal and vertical control in the area. | Use planimetric and topo information captured by the preliminary survey during the design phase. | Existing Centerline: a) Provide record boundary information to be used by Field Survey when locating front pins and property boundaries | Manual Traffic Count (Turning Movements) | Extract from ESD and request any field survey.
Preliminary X-Section |  | Establish preliminary roadway section based on field data located by Survey and from the basic criteria used for street design. |  | Provide existing/proposed lane configuration
Pavement Section | Check Paved Streets Book for existing section. | Typical section is defined but Pavement design is not done at this stage of the project. | Identify any possible ROW needed. | Proposed Signals and Lighting, and Striping
ADTs and formal Project Memo |  |  |  | Current ADT, 20 yr ADT, Commercial
Phase I Report | [6 empty] | Request for Phase I (Geotechnical & Environmental). Retrieve Contaminated Sites from ESD. Notify all Utilities of project activity.
ROW Discrepancies | Locate property irons at intersections. |  | Property Boundary from field Survey, ESD Data, Flag Any Discrepancies. | Provide existing/proposed lane configuration
Owner Names |  |  | Listing of Adjoining owners from ESD
Ownership @ ROW |  |  | Listing of Adjoining owners from ESD
Special Assessment Sheet |  |  | Flag Any Discrepancies. SHPO - Gives a report on historical Status (Federal Fund) - Proj. Eng. HPC - Local Historical fund - Proj. Eng. COE-Status of Flood |  |  |  | Request for Phase I (Geotechnical & Environmental). Retrieve Contaminated Sites from ESD. Notify all Utilities.

## 60%
60%
Disciplines/Deliverables | Survey/Data Capture | Street | ROW | Traffic | Sewer | Water | Utilities/LAB
QA & QC W/Peers of everything.
ROW Encroachments, Easements |  | Locate and plot on Plan sheets | 1) Identify Encroachments and Easements 2) Initiate legal process to levy assessments 3) Historical Abstracting as needed. | Identify additional easement needs based on improvements. Drive survey completed. | Identify easement needs. | Identify easement needs. | Identify easement needs.
Hydraulic Conditions |  |  |  |  | Use HEC, XP SWIM and whatever other analysis software necessary to review hydraulic conditions. | If the improvements will greatly increase water usage, use KYPIPE or whatever other analysis software necessary to review hydraulic conditions.
Define Special Assessments | Located and plotted on Plan Sheets |  | Identify special assessments. | Identify special assessments. | If special sewer system is required, flag the possible need for special assessments. | If special water system is required, flag the possible need for special assessments.
Plan and Profile Sheets | Improvements plotted on Plan and Profile Sheets | Finalize horizontal and vertical alignments. Evaluate plan quantities versus actual quantities. |  |  | Create a separate sewer plan and profiles. | Create a separate water sheet under old conditions. Consider combining this with other sheet(s), if possible. | Add Pavement Design notes to the Plan sheets.
Initiate Assessment Process
Detail Sheets
Notification to Property Owners |  |  |  | Generate Traffic Staging Sheet for Traffic Control.
Traffic Control |  | Determine Lane width and storage capacity. | Generate Traffic Staging Sheet for Traffic Control.
Special Detail Sheets |  | Determine pavement conditions and define removal versus excavation. |  |  |  | Provide any details of water improvements that are not typical. | Pavement Design is completed in Lab.
Erosion Control Sheets |  |  |  |  | Define any special controls needed due to proposed drainage improvements.
Signing Sheet
Striping Sheet
Signals and Light Sheet
Phase I completed |  | Review Phase I report from Lab relative to design |  |  |  |  | Lab provides a Phase I report to the Project Engineer.
Phase II started | [6 empty] | Lab begins the Phase II analysis.

## 90%
90%
Disciplines/Deliverables | Survey/Data Capture | Street | ROW | Traffic | Sewer | Water | Utilities/LAB
Final Plan Sets | Re-verify control as needed. | Finalize Design & Drafting | Finalize Easements and takes | Finalize Sheets | Finalize Design & Drafting | Finalize Design & Drafting
100% Quantities |  | Finalize Quantities |  | Finalize Quantities. | Finalize Sheets & Quantities. Begin submittal of permit applications. | Finalize Sheets & Quantities. | Clarify quantity info using information from Phase II report.
Cost Target confirmation |  | Project Engineer develops this based on the Plan and Profile Sheets
Signal Justification Report (SJR) |  |  |  | Finalize report
Bid Document prepared
Response Action Plan for Soil Issues | [6 empty] | Finalize Phase II and the Response Action Plan
Phase II delivered. |  |  | Completed assessments |  |  |  | Finalize Phase II and the Response Action Plan
QA and QC for all groups | QA/QC of design and plans | QA/QC of design and plans |  | QA/QC of design and plans | QA/QC of design and plans | QA/QC of design and plans
Complete Cooperative Agreement Plan with other Departments.
Notification to Utility Department |  |  | Send notice of public hearing to property owners |  |  |  | Notify utilities of Project Schedules
Notify utilities of Project Schedules