## Slide 1
1st Ave S Reconstruction Project
E. Grant St – E. Franklin Ave.
Stakeholder Meeting
May 1st, 2026

## Slide 2
Project Layout
Project Layout
1st Ave S Reconstruction Project

## Slide 3
CenterPoint Energy – Upgrading gas mains and service connection.
Grant to 94 Bridge: Completed
94 Bridge to Franklin: In progress
  Centerpoint anticipates to be done in the week of 4th of May.
  To expect work with E 18th St. for Steel Pipe reroute that will be coordinated with City Contractor for 1st Ave S Reconstruction Project.
  Centerpoint Website: www.centerpointenergy.com/construction
    Stevens Square – Loring Heights Neighborhood
    Contact: (612) 542-6198 or mnconstruction@centerpointenergy.com
1st Ave S Reconstruction Project
Current Activities
City Project – Construction in progress
Grant to 94 Bridge:
  Removals – in progress between North of I-94 Bridge to 14th St.
  Utility work – Sanitary Sewer Installation is in progress.
  Temporary access route provided for Substance, Event Center and Stradford Flats (Garbage pickup, & Parking Lot users)
18th St to South of I-94 Bridge:
  Staging & prep work - ongoing

## Slide 4: 1st Ave S Reconstruction Project
  Franklin to South I-94 Bridge Activity

## Slide 5: 1st Ave S Reconstruction Project
  North of I-94 Bridge to Grant St. Activity

## Slide 6
Construction- What to Expect
Roadway Construction: In progress
  Large Construction Equipment
  Uneven ground due to removals and utility installation
  Disruption & Noise
  Dust
  Parking Closures
  Temporary Pedestrian Ramps
  Traffic Impacts
  Business Access
  Construction Substantial Completion: November 15, 2026
1st Ave S Reconstruction Project

## Slide 10: DETOUR ROUTES (Vehicles, Bicycles and Pedestrians)

## Slide 11
Communications
Weekly Friday Meetings 10:00 am – 11:00 am
Weekly Email Updates (GovDelivery)
Neighborhood Meetings
One-on-One Site Visits
Website – Sign up for Updates, Project Engineer & Construction Manager Contact Information
https://www.minneapolismn.gov/government/projects/1st-ave-grant-st/
1st Ave S Reconstruction Project

## Slide 12
Questions & Open Discussion
1st Ave S Reconstruction Project